## Sources
Source | Receipt | Inversion | Test Insert & Review | Insertion | Editing | Release Date | Workdays Receipt to Release | Release Version
NCI Thesaurus
NCI2007_01D | 2007-02-02 | 2007-02-09 | 2007-02-26 | 2007-02-27 | 2007-03-16 | 2007-04-12 | 50 | Meta2007_01D
NCI2007_02C | 2007-03-06 | 2007-03-08 | skip test insertion | 2007-03-28 | 2007-04-06 | 2007-04-18 | 32 | Meta2007_02C
NCI2007_03D | 2007-04-09 | 2007-04-10 | skip test insertion | 2007-04-30 | 2007-05-31 | 2007-06-15 | 50 | Meta2007_03D
NCI2007_04E | 2007-05-11 | 2007-05-16 | skip test insertion | 2007-06-08 | 2007-07-23 | n/a | 0 | n/a
NCI2007_05E | 2007-06-04 | 2007-06-07 | skip test insertion | 2007-07-20 | 2007-07-26 | 2007-08-12 | 50 | Meta2007_05E
NCI2007_06D | 2007-07-10 | 2007-08-08 | 2007-08-21 | 2007-08-22 | 2007-08-31 | 2007-09-12 | 47 | Meta2007_06D
NCI2007_07C | 2007-08-20 | 2007-08-22 | skip test insertion | 2007-09-19 | 2007-10-01 | 2007-10-12 | 40 | Meta2007_07C
NCI2007_08D | 2007-09-25 | 2007-08-26 | skip test insertion | 2007-10-03 | 2007-10-15 | n/a |  | n/a
NCI2007_09D | 2007-10-18 | 2007-10-24 | skip test insertion | 2007-11-15 | 2007-11-19 | 2007-12-17 | 43 | Meta2007_09D
NCI2007_10D | 2007-11-12 | 2007-11-13 | skip test insertion | 2007-12-05 | 2007-12-19 | 2008-01-31 | 57 | Meta2007_10D
NCI2007_12A | 2007-12-11 | 2007-12-13 | skip test insertion | 2007-12-24 | 2008-01-14 | n/a |  | n/a
NCI2007_12E | 2008-01-07 | 2008-01-08 | skip test insertion | 2008-03-13 | 2008-03-27 | 2008-04-14 | 69 | Meta2007_12E
NCI2008_01D | 2008-02-06 | 2008-02-08 | skip test insertion | 2008-03-27 | 2008-04-04 | n/a |  | n/a
NCI2008_02D | 2008-03-04 | 2008-03-11 | skip test insertion | 2008-04-02 | 2008-04-15 | 2008-04-30 | 42 | Meta2008_02D
NCI2008_03D | 2008-04-07 | 2008-04-08 | skip test insertion | 2008-06-24 | 2008-06-27 | 2008-07-28 | 79 | Meta2008_03D
NCI2008_04D | 2008-05-09 | 2008-05-09 | skip test insertion | 2008-07-29 | 2008-08-11 | n/a |  | n/a
NCI2008_05D | 2008-06-09 | 2008-06-12 | skip test insertion | 2008-08-08 | 2008-08-21 | n/a |  | n/a
NCI2008_06D | 2008-07-14 | 2008-07-16 | skip test insertion | 2008-08-09 | 2008-08-21 | 2008-09-22 | 50 | Meta2008_06D
NCI2008_07D | 2008-08-01 | 2008-08-06 | skip test insertion | 2008-08-25 | 2008-09-15 | n/a | 0 | n/a
NCI2008_08D | 2008-09-05 | 2008-09-08 | skip test insertion | 2008-09-10 | 2008-09-19 | 2008-10-14 | 28 | Meta2008_08D
NCI2008_09D | 2008-10-09 | 2008-10-15 | 2008-12-04 | 2008-12-05 | in progress
NCI2008_10E | 2008-11-11 | 2008-11-26 | skip test insertion | in progress
NCI Local Sources
CBO2005_06 | 2005-06-20 | 2005-08-26 | 2005-09-01 | 2005-10-31 | 2005-11-15 | 2006-02-08 | 168 | Meta2005_09
MDBCAC2005_12 | 2005-12-27 | 2006-01-10 | 2006-01-22 | 2006-01-23 | 2006-01-26 | 2006-02-16 | 38 | Meta2005_10E
CBO2006_03 | 2006-04-11 | 2006-04-24 | 2006-06-12 | 2006-06-19 | 2006-07-17 | 2006-08-07 | 85 | Meta2006_05D
MDR90 | 2006-05-22 | 2006-05-24 | 7/17/1006 | 2006-07-24 | 2006-09-29 | completed | 0 | Meta2006_06E
MDRSPA90 | 2006-05-24 | 2006-05-25 | 2006-07-17 | 2006-08-02 | 2006-09-29 | n/a | 0 | n/a
ICDO3 | 2006-09-05 | 2006-09-19 | n/a | 2006-09-24 | 2006-09-29 | completed | 0 | Meta2006_06E
PDQ2006_12 | 2006-12-04 | 2006-12-07 | 2006-12-28 | 2006-12-29 | 2007-01-17 | 2007-02-07 | 48 | Meta2006_11D
PMA2007 | 2006-10-18 | 2006-11-26 | 2006-11-28 | 2006-11-29 | 2006-12-04 | 2006-12-29 | 53 | Meta2006_10D
MGED2006_11_08 | 2006-12-06 | 2007-03-02 | 2007-03-12 | 2007-03-22 | 2007-04-06 | 2007-04-18 | 96 | Meta2007_02C
PDQ2007_05 | 2007-05-08 | 2007-05-16 | 2007-06-20 | 2007-07-30 | 2007-08-31 | 2007-09-12 | 92 | Meta2007_06D
CBO2007_06 | 2007-07-17 | 2007-08-20 | 2007-08-27 | 2007-09-05 | 2007-10-01 | 2007-10-12 | 64 | Meta2007_07C
PDQ2007_11 | 2007-11-12 | 2007-11-15 | 2007-12-10 | 2007-12-12 | 2007-12-20 | 2008-01-31 | 57 | Meta2007_10D
RADLEX20 | 2007-12-05 | 2008-01-30 | 2008-04-18 | 2008-04-23 | 2008-06-27 | 2008-07-28 | 164 | Meta2008_03D
PDQ2008_06 | 2008-06-06 | 2008-06-19 | 2008-07-14 | 2008-07-28 | 2008-08-11 | 2008-09-22 | 75 | Meta2008_06D
RADLEX2_01 | 2008-07-28 | 2008-09-17 | 2008-12-01 | 2008-12-02 | 2008-12-15 | in progress
CBO2008_01 | 2008-06-06: in progress
RADLEX21 | 2008-06-06: in progress
0
UMLS Metathesaurus | [6 empty] | 0
UMLS 2005AC | 2005-12-19 | 2006-01-13 | 2006-03-22 | 2006-04-03 | 2006-06-12 | 2006-07-24 | 156 | Meta2006_03D
UMLS2006AA | 2006-06-22 | 2006-07-09 | 2006-08-14 | 2006-08-24 | 2006-09-29 | completed | 0 | Meta2006_06E
UMLS2006AB | 2006-09-18 | 2006-12-05 | 2007-02-12 | 2007-02-26 | 2007-03-16 | 2007-04-12 | 149 | Meta2007_01D
MTH2006AC | 2007-01-08 | 2007-02-23 | 2007-04-03 | 2007-04-18 | 2007-05-31 | 2007-06-15 | 115 | Meta2007_03D
MTH2006AD | 2007-04-16 | 2007-04-30 | 2007-05-25 | 2007-06-18 | 2007-07-23 | 2007-08-13 | 86 | Meta2007_05E
MTH2007AA | 2007-05-07 | 2007-06-01 | 2007-10-15 | 2007-10-21 | 2007-11-13 | 2007-12-17 | 161 | Meta2007_09D
MTH2007AB | 2007-07-10 | 2007-11-26 | 2008-01-08 | 2008-01-22 | 2008-03-27 | 2008-04-14 | 197 | Meta2007_12E
MTH2007AC | 2007-11-28 | 2008-02-19 | 2008-09-15 | 2008-09-30 | 12/15/1008 | in progress
MTH2008AA | 2007-07-10: 2008-04-25; 2007-11-26: 2008-10-10; 2008-01-08: in progress
META RELEASE | EXPORT | BUILD | LOAD | FTP |  |  | Workdays EXPORT to FTP
Meta2005_09 | 2006-01-24 | 2006-02-07 | 2006-02-07 | 2006-02-08 |  |  | 12
Meta2005_10E | 2006-02-13 | 2006-02-15 | 2006-02-16 | 2006-02-16 |  |  | 4
Meta2005_12F | 2006-03-13 | 2006-03-14 | 2006-03-14 | 2006-03-14 |  | 0 | 2
Meta2006_01C | 2006-04-03 | 2006-04-05 | 2006-04-05 | 2006-04-05 |  |  | 3
Meta2006_02D | skip export | n/a | n/a | n/a |  |  | n/a
Meta2006_03D | 2006-06-26 | 2006-07-24 | 2006-07-24 | 2006-07-24 |  |  | 21
Meta2006_05D | 2006-08-02 | 2006-08-07 | 2006-08-07 | 2006-08-07 |  |  | 4
Meta2006_06E | 2006-10-09 | completed | completed | completed |  |  | 0
Meta2006_09D | 2006-11-10 | 2006-12-08 | 2006-12-08 | 2006-12-08 |  |  | 21
Meta2006_10D | 2006-12-21 | 2006-12-29 | 2006-12-29 | 2006-12-29 |  |  | 7
Meta2006_11D | 2007-01-25 | 2007-02-07 | 2007-02-07 | 2007-02-07 |  |  | 10
Meta2007_12D | skip export | n/a | na/ | n/a |  |  | n/a
Meta2007_01D | 2007-03-26 | 2007-04-12 | 2007-04-12 | 2007-04-12 |  |  | 14
Meta2007_02C | 2007-04-13 | 2007-04-18 | 2007-04-18 | 2007-04-18 |  |  | 4
Meta2007_03D | 2007-06-11 | 2007-06-15 | 2007-06-15 | 2007-06-15 |  |  | 5
Meta2007_05E | 2007-08-03 | 2007-08-13 | 2007-08-13 | 2007-08-13 |  |  | 7
Meta2007_06D | 2007-09-07 | 2007-09-12 | 2007-09-12 | 2007-09-12 |  |  | 4
Meta2007_07C | 2007-10-09 | 2007-10-12 | 2007-10-12 | 2007-10-12 |  |  | 4
Meta2007_08D | skip export | n/a | n/a | na |  |  | n/a
Meta2007_09D | 2007-12-12 | 2007-12-17 | 2007-12-17 | 2007-12-17 |  |  | 4
Meta2007_10D | 2008-01-28 | 2008-01-31 | 2008-01-31 | 2008-01-31 |  |  | 4
Meta2007_12E | 2008-03-31 | 2008-04-14 | 2008-04-14 | 2008-04-14 |  |  | 11
Meta2008_02D | 2008-04-25 | 2008-04-30 | 2008-04-30 | 2008-04-30 |  |  | 4
Meta2008_03D | 2008-07-21 | 2008-07-28 | 2008-07-28 | 2008-07-28 |  |  | 6
Meta2008_04D | skip export | n/a | n/a | n/a |  |  | n/a
Meta2008_05D | skip export | n/a | n/a | n/a |  |  | n/a
Meta2008_06D | 2008-09-08 | 2008-09-22 | 2008-09-22 | 2008-09-22 |  |  | 11
Meta2008_07D | skip export | n/a | n/a | n/a |  |  | n/a
Meta2008_08D | 2008-10-09 | 2008-10-14 | 2008-10-14 | 2008-10-14 |  |  | 4
rebuild of Meta2008_08D | 2008-10-31 | 2008-11-06 | 2008-11-06 | 2008-11-06 |  |  | 5
Meta2008_09D | 2007-07-10: in progress
Formulas:
Workdays Receipt to Release = IF(ISERROR(NETWORKDAYS([Receipt],[Release Date],Holidays!$A4:A23)),0,IF(NETWORKDAYS([Receipt],[Release Date],Holidays!$A4:A23)>0,NETWORKDAYS([Receipt],[Release Date],Holidays!$A4:A23),0))
Workdays Receipt to Release = IF(ISERROR(NETWORKDAYS([Receipt],[Insertion],Holidays!$A4:A23)),0,IF(NETWORKDAYS([Receipt],[Insertion],Holidays!$A4:A23)>0,NETWORKDAYS([Receipt],[Insertion],Holidays!$A4:A23),0))
Note on F3: squan: 2/12/2007 NCI will be test inserted after UMLS2006AB Part III has been inserted. 2/23/2007 Had a db available so test inserted. 2/25/07 test insertion completed.
Note on G3: squan: 2/27/07 Insertion completed.
Note on H3: squan: 3/5/07 editing should be completed by this Friday.
Note on D4: squan: 3/5/07 Carol C. running ExportRels.
Note on F4: squan: 3/12/07 Carol to check w/Laura whether it should be inserted at the same time as MGED or inserted later on. 3/26/07 ready to start test insertion. 3/27/07 Skip test insertion. Start with real insertion.
Note on G6: quans: 5/14/07 Insertion done after export.
Note on G7: quans: 6/18/07 NCI will let us know when they are ready for us to insert. 7/19/07 Begin insertion tonight after 5pm.
Note on E8: quans: 7/12 Questions about new subsources and ATNs that have been omitted from the configuration file. NCI checking into this. 8/6/07 Waiting for a citation for subsource ICH.
Note on F8: quans: 8/20/07 Test insertion complete and review underway.
Note on G9: quans: 9/17 To be inserted either Tues or Wed.
Note on G11: quans: 10/29/07 Wait for editing counts to decrease before inserting. 11/5/07 insert possibly Mon or Tues (11/12-13) before next export 11/14/07 Insertion started.
Note on G13: quans: 12/21 insertion started
Note on G15: quans: 3/24 To be inserted at the end of this week once editing is completed.
Note on H15: quans: 3/31 Editing should be complete by the end of the week.
Note on E16: quans: 3/4 Data problem with source and termtype values switched. Sent file of affected records to NCI. 3/6 Received fixed file. Inversion started.
Note on H16: quans: 4/7 Editing still in progress. Expect to be finished next week. 4/14 Editing should be complete by tomorrow.
Note on D17: quans: 4/7 Original data received on 4/4 but the value of the source and termtype fields switched. Corrected data received today.
Note on G17: quans: 4/28 Will wait until Radlex editing decreases before inserting. 6/23 Insertion started. 6/24 Insertion completed. Review underway.
Note on G18: quans: 7/28 Insertion started. 7/29 Insertion complete. Review in progress.
Note on G21: quans: 8/22 Insertion planned for Monday, 8/25.
Note on D22: Quan, Sharon L: 11/11 Possible problem with CDISC code for 3 atoms. NCI looking into it .
Note on E23: quans: 10/10 Error when importing and classifying file into TDE. Looking into the problem. 10/13 Problem is that the data only has "NCI_Kind" but the domain and range uses other kinds. 10/14 Changed to domain and range fields to 'NCI_Kind' and started inversion.
Note on F23: Quan, Sharon L: 11/17 Waiting for editing to decrease before inserting. Include in next export. 11/24 To be inserted next week. 12/1 To be inserted today. 12/2 Test insertion completed. Under review.
Note on E24: Quan, Sharon L: 11/11 Possible problem with CDISC code for 3 atoms. NCI looking into it. 11/17 Changing CDISC records back to the way they were in 09D. 11/19 Only change the 3 CDISC records that had their code changed. Keep all other changes. 11/21 Question about role groups leading to duplicate RUIs. Waiting for NCI response. 11/24 Will go ahead and create relationships with rolegroups and populate the SRUI field.
Note on F24: Quan, Sharon L: 12/8 Will discuss whether to insert 10E by year's end for an export at next Monday's meeting.12/15 Skip test insertion even though SRUIs new to this version.
Note on E28: Time includes waiting for new relationship files, sty assignments, finalizing source inversion proposal, etc.
Note on E30: 4/12 sent NCI and Cerner proposal and source information for review. 4/21 Data error in cbo_terms.csv file. Manually corrected file and re-ran scripts.
Note on F30: Apelon: 5/22 Currently being reviewed. Real insertion will take place after editing of UMLS2005AC is complete.
Note on G30: Apelon: 6/19 problems found with insertion. Corrections made.
Note on H30: Apelon: 6/26 Difficulty in editing b/c there is nothing to indicate which Sys are connected to which PTs. To resolve, Apelon will recreate a classes_atoms.src file and insert scui and saui codes. 6/27 scui and saui codes updated.
Note on F31: Apelon: 6/19 test insert MDR again. 6/26 test insertion complete. 7/9 under review.
Note on G31: Apelon: 7/17 source will be inserted after the export of Meta2006_05D.
Note on H31: Apelon: 8/14 being edited.
Note on F32: Apelon: Test insertion complete on 6/1.
Note on G32: Apelon: 7/17 source will be inserted after the export of Meta2006_05D.
Note on H32: Apelon: 8/14 being edited.
Note on I32: squan: Spanish terms are not currently being included because of a problem Metaphrase has handling foreign language terms.
Note on E33: Apelon: 9/8 Inversion complete. 9/18 Found that SAIDs were overlapping due to an error in a previous source. 9/19 Re-inverted source with new SAIDs.
Note on D34: squan: Questions about data format. Seeing end of line characters within records. Asked NCI about it. 12/4 We are going to go ahead with the inversion and try to fix the data ourselves since we haven't heard back re: the data format problems yet.
Note on E35: MSD: There were many problems with the encoding of the data. Had to translate an Excel file to cp1252 then to utf8. Needed to remove bullets and other control characters resulting from the Excel format, needed to translate unicode characters to ascii.
Note on D37: quans: 4/10/07 Received April data. 5/8/07 Decided to use May data instead. Changed SAB to PDQ2007_05.
Note on E37: squan: 4/11/07 sent PDQ2007_04 source inversion proposal to NCI. Waiting for feedback. 5/7/07 SLQ will start inversion this week. 5/8/07 Decided to use May data rather than April's. Changed SAB to PDQ2007_05.
Note on F37: quans: 5/14/07 Can be test inserted after the db has been turned over to Brian. 6/8/ Test insertion complete. Under review. 6/18/07 Reviewing test insertion.
Note on G37: quans: 6/20/07 Wait to hear from NCI before inserting. 7/9/07 Per Sherri, we'll export the db again before inserting PDQ.
Note on E38: quans: 7/19/07 Before continuing with inversion , NCI will decide if they want to update this source. 8/13/07 Begin inversion process.
Note on G38: quans: 8/27 Wait until editing cycle is complete before inserting CBO.
Note on E39: quans: 11/12/07 Will start inversion after NCI2007_10D complete.
Note on E40: quans: 1/24 Conference call with Sherri to discuss data and source inversion proposal.
Note on F40: quans: 1/24 Will fill in sources.src with temp. data for test insertion. Will update with official data when received. 2/4 Two files sent: one of data issues and one a list of attributes with their values/domains. Being reviewed by NCI. 2/6 Meeting with Daniel R. to discuss data issues. Working on identifying every RADLEX record affected for each data issue found. 2/12 Sent file of all affected records to Daniel and Sherri. 2/13 Daniel asks to wait until they fix data before test inserting. 3/10 Unknow when corrections will be made. May test insert next week after demotions have gone down. 3/17 After 12E export, will copy db and test insert. Corrections not received yet. 4/2 Test insertion completed. 4/7 Under review. 4/10 2nd test insertion started. 4/14 AS termtype causing inappropriate merging. Will exclude AS from merging. Re-running test insertion. 4/16 Radlex test insertion completed.
Note on H40: quans: 6/2 Demotion editing completed. 7000 concepts for regular editing remain. 6/9 6000 concepts needing editing remain.6/16 4800 concepts needing editing remain.
Note on D41: quans: 6/2 Will retrieve data files once its available.
Note on F41: quans: 6/27 Test insertion complete. 7/8 Test insertion review completed.
Note on G41: quans: 7/15 Real insertion to be done next week. 7/21 Real insertion will be done sometime this week. 7/26 Real insertion complete. Under review.
Note on C42: quans: 9/2 This SAB is temp. Sherri is checking to see what vesion RADLEX has assigned to this.
Note on E42: quans: 8/11 In contact with Beverly Collins to resolve data problems . 8/15 Draft of primary inversion complete. Waiting to receive new file of corrections. 8/25 Received corrected data. Will QA it and use it for the inversion. 8/29 QA revealed data problems such as self-referential relationships and a structural problem in one of the entries. RADLEX looking into problem and will send another file. 8/29 New file received. 9/5 Si_proposal sent for review.
Note on F42: quans: 9/22 Test insertion after MTH2007AC review complete. 10/27 Wait for editing to wind down before test inserting. 11/3 Editing continues. Wait until MEME db cleaner before test inserting. 11/17 Editing continues. Wait before inserting. Plan to include in next export. 11/24 To be test inserted coming Tuesday. 11/26 Test insertion complete. Under review. 12/1 Real insertion tonight.
Note on D43: Quan, Sharon L: 12/8 Source will arrive in January 2009
Note on D44: Quan, Sharon L: 12/8 Source will arrive in Jan. 2009
Note on F48: 2/3/06 - Test insertion of 2005AC continues. We had to temporarily stop it due to the large volume of activity during the insertion which was slowing down preparations for the export and NCI2005_12F insertion. 2/14/06 the disk configuration on cbioapp513 is not optimal for Oracle; the inversion files had left off a field from classes_atoms.src file that is needed for the CUI assignment which is very important for the UMLS update; we have refreshed the DB, re-inverted the classes file and will proceed with the test insertion (again). 3/6 2005AC inversion is being redone to include "suppressible" atoms from the UMLS. The algorithm used to remove certain term types when generating the UMLS subset for the NCI update caused all suppressible atoms including RXNORM/OCD,OBD to be left out. This involves starting with UMLS files and generating the relevant subset and re-inverting the files. 3/9 UMLS_CUI attributes for the existing UMLS data were inserted. This will assist in handling the UMLS 2005AC update properly.
Note on G48: 4/10 MTH attributes inserted and SNOMED concepts assembled
Note on F50: squan: 1/8 part I of test insertion (MSH) complete; beginning part II (SNOMEDCT) begins 1/9. 1/12 test insertion complete. Review in progress. 1/23 Test insertion for part III. 1/25 Bug found in scripts for part III. Test insertion re-started. 1/28 Part III under review. Part I real insertion this weekend.
Note on G50: squan: 2/3 Real insertion of Part I started. 2/5 Part I complete. 2/8 Real insertion of Part II started.l 2/12 Part II complete. Part III will be inserted when editing of Part II is finished. 2/16 Part III real insertion started. 2/21 Part III insertion complete and review underway.
Note on E51: squan: 2/23 re-run of MTH2006AC for NCI with SCTSPA moved from part3 to part2
Note on F51: squan: 3/19/07 part I test insertion complete. 3/20/07 part I test insertion review complete. 3/26/07 Start part II test insertion this week 3/30/07 Part II test insertion and review completed. 3/30/07 Start Part III test insertion. 4/2/07 Part III test insertion complete. 4/3/07 Part III review complete.
Note on G51: squan: 4/9/07 will insert all 3 parts before returning db. Est. completion is Wed., 4/11. 4/12/07 Part I insertion and review complete. 4/14/07 Part II insertion complete and Part III in progress 4/16/07 Part III complete and under review.
Note on F52: quans: 5/9/07 Part I test insertion complete. 5/17/07 Part II test insertion complete. 5/18/07 Part III test insertion complete. 5/23/07 Review in progress.
Note on G52: quans: 5/25/07 Wait until after export to do real insertion. 6/11/07 Part I insertion complete. 6/13/07 Part II insertion completed. 6/18/07 Part III insertion completed.
Note on F53: quans: 9/17 To be test inserted this week. 9/25/ Test insertion complete.
Note on F54: quans: 12/13/07 test insertion started. 12/17/07 Part I complete. Part II in progress. 12/21/07 Part II in progress. 12/27/07 Test insertion complete. Under review.
Note on G54: quans: 1/10/08 Part I complete. 1/14/08 Part II complete. 1/17/08 Insertion complete but there are count discrepencies with what was in the test insertion.
Note on H54: quans: 1/28 Expect editing to be completed in 2-3 weeks.
Note on E55: quans: 2/4 Sherri will check to see if any feedback received on replacing MDR90 with MDR10. 2/15 Sherri checking with Frank re: any feedback. 2/19 Inversion complete using MDR10.
Note on F55: quans: 3/31 AC test insertion can be done after the RADLEX test insertion. 4/14 Test insertion after the 200802 export. 5/12 May re-run part of inversion to remove SCTSPA. Test insertion will follow. 5/16 MDRSPA and SCTSPA removed from db. Inversion files re-created to remove SCTSPA. Part 1 of test insertion complete. Part II underway. 5/19 Part II is complete. Part III started. 5/29 Part III performing merge sets. 6/2 Problem with the merge set step. LM will have to identify problem and restart the merge. Also, the test insertion will be re-run b/c of too many quick fixes during this test insertion. 6/9 Still having problems with the merge set in part III. Plan is to just start the test insertion all over from the beginning with a re-freshed db. 6/10 Part I of the test insertion started again. 6/11 Part I complete. Part II started. 6/16 Part II complete and Part III started. 6/20 Part III complete. Review underway. 7/10 Review continues. 8/18 Will resolve problem caused by incorrect low_source and re-run test insertion this week. 8/25 Test insertion do be done this week or over Labor Day weekend. 8/30 Part 1 of test insertion started. 9/2 Part I of test insertion completed. 9/3 Part II test insertion started. 9/8 Part II completed. 9/15 Part III test insertion completed.
Note on G55: quans: 9/23 Part I insertion started. 9/24 Part I completed. Part II started. 9/29 Part III started. 9/30 Part III completed.
Note on H55: quans: 10/6 Editing will take approx. 3 weeks.
Note on D60: Waited until PDQ2005_12 editing was complete before beginning export.
Note on E60: Ran out of space on 1/26/06. Build has to be re-started. Build finished 1/27. Sharon out. Build checked 1/30 and files being sent. Being put in test database 1/30. Problem discovered with hierarchy 1/31/. MRCXT and MRREL corrected and build rerun on 2/2. 2/2-2/3/06 - Problem with 'no record locks'. 2/6/06 - Still working on record lock problem. Meeting with Sherri today. Resolved problem in the pm. Scripts ran overnight. 2/7/06 Created concept.out files.
Note on F60: 1/30 CBO codes too long for code field in Oracle table. Corrected and rebuilt mphdata.zip file. Data loaded into test database. Created concept.out reports but found problem with the relationships of the higher level concepts. No hierarchical tree displaying. 1/31 Will correct the relationship files and rebuild. 2/6/06 - Second attempt at load on hold until 'lock' problem resolved. Lock problem resolved. 2/7/2006 Data loaded into test db.
Note on G60: 2/9/06 Noticed no NCI definitions included in build. Apelon buillt new condef.dat file and ftp'd to NCI so they could update their files.
Note on D61: File being collected 1/31/06. 2/9/06 Export essentially complete. Need to copy back files to Apelon for the build and create the history and mapping files.
Note on D65: Apelon: Export is a little behind schedule because of some tricky issues related to the way the MTH update works and because the parallel operations with the MEMEDB cleanup are making the machine quite slow.
Note on E65: Apelon: 7/5 encountered core dump and out of memory error messages.7/9 build completed over the weekend; files being zipped. 7/11 context.dat file to large to zip. Need to split files. 7/13 Split successfully done but found context.dat not correct. Nels edited script to split MRCXT which is used in creating context.dat. New context.dat created. Also going to try processing files on cbioapp513 since it has more memory/space than Apollo. 7/14 -7/21 Encountered additional problems of extra end of line characters, UMLS SAB contained a "." (period) which is not allowed in Metaphrase. Some scripts need to be re-written. 7/24 Scripts completed. Portion of build run over the weekend. Building mphdata files.
Note on D67: Apelon: Export started 10/6/2006
Note on E68: squan: 12/4 Waiting for atlas to be setup so that the concept.out files can be created.
Note on D72: squan: 3/9/07 start export 3/12/07 editing continues; start export at end of week 3/19/07 db ready for export
Note on E72: squan: 3/27/07 migration of data to cbioatlas /d1 directory not complete yet. Should be ready by next week and then can start build. 4/3/07 /d1 and /d2 directories now ready.
Note on D73: squan: 4/6/07 DB ready for export. 4/8/07 Export started.
Note on D74: quans: 5/31/07 Editing complete. Db ready for export. 6/4/07 Export running.
Note on D75: quans: 7/24/07 DB ready to begin export. 7/24/07 DB still has some concepts that require editing. (These did not show up due to bug in EMS). DB returned. 7/26/07 Editing complete. 7/27/07 Export beginning.
Note on D80: quans: 12/19 db ready for export. 1/24 Export still in progress.
Note on D81: quans: 3/31 RRF files currently being built.
Note on D82: quans: 4/7 Export to start next week.4/18 Export in progress.
Note on C83: quans: 4/28 Export will incl. RADLEX and NCIt. MTH insertion on hold. 6/2 Export will be done within the next couple of weeks. PDQ2008_06 will not be incl.
Note on D83: quans: 6/28 Pre-production step started: cleaning up MID validation issues. 7/2 Pre-production still in progress. 7/9 Pre-production complete. 7/10 Production in progress.
Note on C86: quans: 10/17 STY problems found in UMLS data affected build. However, build will not be re-done.
Note on D86: quans: 8/22 Pre-production steps completed. 8/25 DB will be returned tomorrow, 8/26. 9/5 Running MRCXT. 9/8 Export completed.
Note on E86: quans: 9/15 MRSO and MRREL files had the RSAB instead of the VSAB. Files recreated.
Note on D88: quans: 9/29 Export operations to start tonight or tomorrow. 10/3 Export started. 10/6 Export will finish in a couple of days.
Note on C89: quans: 10/17 Due to STY problems found in UMLS data, 0808D will need to be rebuilt 10/27 Rebuild started. 10/28 MRSTY file not complete. Cancel rebuild. 10/31 Files ready. Start build once more.
Note on E89: Quan, Sharon L: 11/3 Build in progress.
Note on D90: Quan, Sharon L: 12/8 NCI will be ready for an export by end of year. 12/15 Export tentatively scheduled for Friday, 12/19.

## MEME
| Priority | Completion Date | Progress Notes
Maintenance Work
Export preparations and DB cleanup | High | 2008-12-12 | 200809 Export (estimated)
MID Validation & Monster QA | High | 2008-12-08 | Finished for 12/1/2008
Documentation |  |  |  | 0
Editing Support
Miscellaneous
Install LVG2009 from NLM when ready | Med | 2008-12-15 | lvg2009 is currently in pre-release mode.
Switch NCI-MEME when it is officially released.
Update to latest NLM code | Med | 2008-12-12 | Make sure "prod mid cleanup" is fixed in NLM code.
Note on E3: Brian Carlsen: Estimated
Note on E4: Joanne Wong: Estimated

## Meta Releases
| META2008_08D (rebuild) | META2008_06D | META2008_03D | META2008_02D | META2007_12E | META2007_10D | META2007_09D | META2007_07C | META2007_06D
UMLS Meta base | MTH2007AB | MTH2007AB | MTH2007AB | MTH2007AB | MTH2007AB | MTH2007AA | MTH2007AA | MTH2006AD | MTH2006AD
NCI Thesaurus version | NCI2008_08D | NCI2008_06D | NCI2008_03D | NCI2008_02D | NCI2007_12E | NCI2007_10D | NCI2007_09D | NCI2007_07C | NCI2007_06D
Local Sources* | BioC_0808D | BioC_0806D | BioC_0803D | BioC_0802D | BioC_0712E | BioC_0710D | BioC_0709D | BioC_0707C | BioC_0706D
| CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2007_06 | CBO2006_03
| CDC_0808D | CDC_0806D | CDC_0803D | CDC_0802D | CDC_0712E | CDC_0710D | CDC_0709D | CDC_0707C | CDC_0706D
| CDISC_0808D | CDISC_0806D | CDISC_0803D | CDISC_0802D | CDISC_0712E | CDISC_0710D | CDISC_0709D | CDISC_0707C | CDISC_0706D
| COH_0808D | COH_0806D | COH_0803D | COH_0802D | COH_0712E | COH_0710D | CRCH_0709D | CRCH_0707C | CRCH_0706D
| CRCH_0808D | CRCH_0806D | CRCH_0803D | CRCH_0802D | CRCH_0712E | CRCH_0710D | CTCAE_0709D | CTCAE_0707C | CTCAE_0706D
| CTCAE_0808D | CTCAE_0806D | CTCAE_0803D | CTCAE_0802D | CTCAE_0712E | CTCAE_0710D | CTEP04 | CTEP04 | CTEP04
| CTEP04 | CTEP04 | CTEP04 | CTEP04 | CTEP04 | CTEP04 | DCP_0709D | DCP_0707C | DCP_0706D
| DCP_0808D | DCP_0806D | DCP_0803D | DCP_0802D | DCP_0712E | DCP_0710D | DICOM_0709D | DTP_0707C | DTP_0706D
| DICOM_0808D | DICOM_0806D | DICOM_0803D | DICOM_0802D | DICOM_0712E | DICOM_0710D | DTP_0709D | ELC2001 | ELC2001
| DTP_0808D | DTP_0806D | DTP_0803D | DTP_0802D | DTP_0712E | DTP_07010D | ELC2001 | FDA_0707C | FDA_0706D
| ELC2001 | ELC2001 | ELC2001 | ELC2001 | ELC2001 | ELC2001 | FDA_0709D | ICDO3 | ICDO3
| FDA_0808D | FDA_0806D | FDA_0803D | FDA_0802D | FDA_0712E | FDA_0710D | ICDO3 | ICH_0707C | ICH_0706D
| ICDO3 | ICDO3 | ICDO3 | ICDO3 | ICDO3 | ICDO3 | ICH_0709D | JAX_0707C | JAX_0706D
| ICH_0808D | ICH_0806D | ICH_0803D | ICH_0802D | ICH_0712E | ICH_0710D | JAX_0709D | KEGG_0707C | KEGG_0706D
| JAX_0808D | JAX_0806D | JAX_0803D | JAX_0802D | JAX_0712E | JAX_0710D | KEGG_0709D | MDBCAC2005_12 | MDBCAC2005_12
| KEGG_0808D | KEGG_0806D | KEGG_0803D | KEGG_0802D | KEGG_0712E | KEGG_0710D | MDBCAC2005_12 | MDR90 | MDR90
| MDBCAC2005_12 | MDBCAC2005_12 | MDBCAC2005_12 | MDBCAC2005_12 | MDBCAC2005_12 | MDBCAC2005_12 | MDR90 | MGED131 | MGED131
| MDR90 | MDR90 | MDR90 | MDR90 | MDR90 | MDR90 | MGED131 | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only)
| MGED131 | MGED131 | MGED131 | MGED131 | MGED131 | MGED131 | NCI-CTCAEv3 (SRC atoms only) | NCI-GLOSS_0707C | NCI-GLOSS_0706D
| NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-CTCAEv3 (SRC atoms only) | NCI-GLOSS_0709D | NCI-HL7_0707C | NCI-HL7_0706D
| NCI-GLOSS_0808D | NCI-GLOSS_0806D | NCI-GLOSS_0803D | NCI-GLOSS_0802D | NCI-GLOSS_0712E | NCI-GLOSS_0710D | NCI-HL7_0709D | NCI2007_07C | NCI2007_06D
| NCI-HL7_0808D | NCI-HL7_0806D | NCI-HL7_0803D | NCI-HL7_0802D | NCI-HL7_0712E | NCI-HL7_0710D | NCI2007_09D | PDQ2007_05 | PDQ2007_05
| NCI2008_08D | NCI2008_06D | NCI2008_03D | NCI2008_02D | NCI2007_12E | NCI2007_10D | PDQ2007_05 | PMA2007 | PMA2007
| PDQ2008_06 | PDQ2008_06 | PDQ2007_11 | PDQ2007_11 | PDQ2007_11 | PDQ2007_11 | PMA2007 | RENI_0707C | RENI_0706D
| PMA2007 | PMA2007 | PMA2007 | PMA2007 | PMA2007 | PMA2007 | RENI_0709D | UCUM_0707C | UCUM_0706D
| RADLEX20 | RADLEX20 | RADLEX20 | RENI_0802D | RENI_0712E | RENI_0710D | UCUM_0709D
| RENI_0808D | RENI_0806D | RENI_0803D | UCUM_0802D | UCUM_0712E | UCUM_0710D
| UCUM_0808D | UCUM_0806D | UCUM_0803D
Special Comments
*new/updated sources highlighted

## Holidays
Federal Holidays
2008
2008-01-01 | LM holiday
2008-01-21
2008-02-18
2008-05-26 | LM holiday
2008-07-04 | LM holiday
2008-09-01 | LM holiday
2008-10-12
2008-11-11
2008-11-27 | LM holiday
2008-11-28 | LM holiday
2008-12-25 | LM holiday